## Task Division + Gantt
Autonomous Vehicle Prototype
Project Task Division with Gantt Timeline
Hamm-Lippstadt University of Applied Sciences ¦ Electronic Engineering
Project supervision |  | Prof. Stefan Henkler / Faezeh Pasandideh/Fatima Idrees/Gido Wahrmann
Team members |  | Amina Boudali, Naved Afridi Rashiq,Tanseem Farwah, Tzuen Lin
[7 empty] | April 2026 | [9 empty] | May 2026 | [30 empty] | June 2026
Project Task Division | [6 empty] | Gantt Timeline
Task Category | Subtask | Task Owner | Start Date | Due Date | Short Summary | Status | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
3D Holders Design | Breadboard & Battery Holder Design | Tanseem Farwah | 2026-04-25 | 2026-04-29 | Design combined holder for battery and breadboard placement | Completed | bar: Gantt Timeline 25 to Gantt Timeline 29; Gantt Timeline 16 to Gantt Timeline 17; Gantt Timeline 23 to Gantt Timeline 24
| Motor Holder Design | Amina Boudali & Tzuen Lin | 2026-04-22 | 2026-05-02 | Create motor mounting support | Completed | bar: Gantt Timeline 22 to Gantt Timeline 3; Gantt Timeline 16 to Gantt Timeline 17; Gantt Timeline 23 to Gantt Timeline 24
| IR Sensor Holder Design | Tzuen Lin | 2026-04-25 | 2026-05-05 | Develop flexible holder for IR sensors | Completed | bar: Gantt Timeline 25 to Gantt Timeline 5; Gantt Timeline 16 to Gantt Timeline 17; Gantt Timeline 23 to Gantt Timeline 24
| Ultrasonic Sensor Holder Design | Naved Afridi Rashiq | 2026-04-22 | 2026-04-29 | Create support for ultrasonic sensors | Completed | bar: Gantt Timeline 22 to Gantt Timeline 29; Gantt Timeline 16 to Gantt Timeline 17; Gantt Timeline 23 to Gantt Timeline 24
System Diagrams | Requirements Diagram | Naved Afridi Rashiq | 2026-05-11 | 2026-05-22 | Define system requirement | Completed | bar: Gantt Timeline 11 to Gantt Timeline 24
| Block Definition Diagram (BDD) | Tanseem Farwah | 2026-05-11 | 2026-05-18 | Show system components and structure | Completed | bar: Gantt Timeline 11 to Gantt Timeline 18; Gantt Timeline 23 to Gantt Timeline 24
| Internal Block Diagram (IBD) | Tanseem Farwah | 2026-05-11 | 2026-05-20 | Represent internal system connections | Completed | bar: Gantt Timeline 11 to Gantt Timeline 20; Gantt Timeline 23 to Gantt Timeline 24
| Use Case Diagram | Tanseem Farwah | 2026-05-14 | 2026-05-24 | Show user and system interactions | Completed | bar: Gantt Timeline 2; Gantt Timeline 14 to Gantt Timeline 24
| Sequence Diagram | Amina Boudali | 2026-05-16 | 2026-05-24 | Represent communication flow | Completed | bar: Gantt Timeline 16 to Gantt Timeline 24
| Activity Diagram | Naved Afridi Rashiq | 2026-05-16 | 2026-05-24 | Describe workflow behavior | Completed | bar: Gantt Timeline 16 to Gantt Timeline 24
| Package Diagram | Tzuen Lin | 2026-05-18 | 2026-05-24 | Organize system elements | Completed | bar: Gantt Timeline 16 to Gantt Timeline 24
Electronics & Circuit Integration | Circuit Design (Tinkercad) | Amina Boudali | 2026-05-11 | 2026-05-15 | Build electronic circuit in TinkerCAD | Completed | bar: Gantt Timeline 11 to Gantt Timeline 17; Gantt Timeline 23 to Gantt Timeline 24
| Arduino Code Development (Tinkercad) | Amina Boudali | 2026-05-11 | 2026-05-15 | Program autonomous vehicle behavior | Completed | bar: Gantt Timeline 11 to Gantt Timeline 17; Gantt Timeline 23 to Gantt Timeline 24
| Power Circuit | Amina Boudali | 2026-04-21 | 2026-05-24 | Design a circuit showing power connections to ensure correct wiring and safe operation. | Completed | bar: Gantt Timeline 16 to Gantt Timeline 17; Gantt Timeline 21 to Gantt Timeline 24
| Wiring & Connection Documentation | Naved Afridi Rashiq | 2026-05-22 | 2026-05-24 |  | Completed | bar: Gantt Timeline 16 to Gantt Timeline 17; Gantt Timeline 22 to Gantt Timeline 24
Assembly | Component Assembly | Naved Afridi Rashiq&Tzuen Lin | 2026-05-11 | 2026-05-24 | Assemble physical components to the chasis | Completed | bar: Gantt Timeline 11 to Gantt Timeline 24
| Wiring & Cable Integration | Amina Boudali | 2026-05-22 | 2026-05-29 |  | Completed | bar: Gantt Timeline 16 to Gantt Timeline 17; Gantt Timeline 22 to Gantt Timeline 24; Gantt Timeline 28 to Gantt Timeline 29